## Honors Thesis Gantt Chart
HONORS THESIS GANTT CHART — Evaluating Google Maps as a Pharmacy Establishment Data Source
Congyuan Zheng (Othello) ¦ Geography Honors Thesis ¦ CU Boulder ¦ April 2026 – November 2026
[8 empty] | April 2026 |  |  |  | May 2026 |  |  |  | June 2026 |  |  |  | July 2026 |  |  |  | August 2026 |  |  |  | September 2026 |  |  |  | October 2026 |  |  |  | November 2026
[8 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
WBS | TASKS AND SUBTASKS | DEP | START | DUE | HOURS | DURATION | % DONE
REGISTRATION & DATA COLLECTION
1 | Honors Program Registration | — | Apr 14 | Apr 22 | 2 hrs | 1 wk | In Progress | bar: April 2026 W1 to April 2026 W2
1.1 | Submit Qualtrics registration form | — | Apr 14 | Apr 22 | 1 hr | 1 day | In Progress | bar: April 2026 W1 to April 2026 W2
1.2 | Confirm Bill Travis email to honors@colorado.edu | — | Apr 14 | Apr 22 | — | 1 day | Done | bar: April 2026 W1
2 | Board of Pharmacy Validation | — | Apr 14 | Apr 27 | 4 hrs | 2 wks | Done | bar: April 2026 W1 to April 2026 W2
2.1 | Purchase & load MN Board of Pharmacy data ($95) | — | Apr 14 | Apr 14 | 1 hr | 1 day | Done | bar: April 2026 W1
2.2 | Run fuzzy matching validation pipeline | 2.1 | Apr 14 | Apr 15 | 2 hrs | 1 day | Done | bar: April 2026 W1
2.3 | Run validity audit (7 audits) | 2.2 | Apr 14 | Apr 15 | 1 hr | 1 day | Done | bar: April 2026 W1
2.4 | Generate figures B1–B5 | 2.3 | Apr 14 | Apr 16 | 1 hr | 2 days | Done | bar: April 2026 W1 to April 2026 W2
3 | NETS Commercial Database Comparison | 2 | Apr 27 | May 10 | 6 hrs | 2 wks | Pending | bar: April 2026 W4 to May 2026 W2
3.1 | Receive NETS data from UA (research team) | — | Apr 27 | Apr 27 | — | 1 day | Pending | bar: April 2026 W4
3.2 | Run NETS vs Board of Pharmacy validation | 3.1 | Apr 28 | May 5 | 3 hrs | 1 wk | Pending | bar: May 2026 W1
3.3 | Finalize Figure B4 (AI vs NETS comparison) | 3.2 | May 6 | May 10 | 3 hrs | 1 wk | Pending | bar: May 2026 W2
WRITING
4 | Literature Review | — | May 1 | Jun 30 | 15 hrs | 8 wks | — | bar: May 2026 W1 to June 2026 W4
4.1 | Pharmacy desert & health equity literature | — | May 1 | May 31 | 6 hrs | 4 wks | — | bar: May 2026 W1 to May 2026 W4
4.2 | GeoAI & LLMs in urban geography literature | — | May 1 | May 31 | 5 hrs | 4 wks | — | bar: May 2026 W1 to May 2026 W4
4.3 | POI data quality & commercial database lit. | — | Jun 1 | Jun 30 | 4 hrs | 4 wks | — | bar: June 2026 W1 to June 2026 W4
5 | Introduction Chapter | 4 | May 15 | Jun 30 | 10 hrs | 6 wks | — | bar: May 2026 W3 to June 2026 W4
5.1 | Research problem & motivation | — | May 15 | May 31 | 4 hrs | 2 wks | — | bar: May 2026 W3 to May 2026 W4
5.2 | Research questions & contributions | 5.1 | Jun 1 | Jun 30 | 6 hrs | 4 wks | — | bar: June 2026 W1 to June 2026 W4
6 | Methodology Chapter | 3 | May 15 | Jun 30 | 12 hrs | 6 wks | — | bar: May 2026 W3 to June 2026 W4
6.1 | AI pipeline architecture documentation | — | May 15 | May 31 | 5 hrs | 2 wks | — | bar: May 2026 W3 to May 2026 W4
6.2 | Validation framework documentation | 6.1 | Jun 1 | Jun 30 | 7 hrs | 4 wks | — | bar: June 2026 W1 to June 2026 W4
7 | Results Chapter | 6 | Jul 1 | Jul 31 | 12 hrs | 4 wks | — | bar: July 2026 W1 to July 2026 W4
7.1 | Board of Pharmacy validation results | — | Jul 1 | Jul 15 | 5 hrs | 2 wks | — | bar: July 2026 W1 to July 2026 W2
7.2 | NETS comparison results | 7.1 | Jul 16 | Jul 31 | 4 hrs | 2 wks | — | bar: July 2026 W3 to July 2026 W4
7.3 | Spatial equity analysis results | 7.2 | Jul 16 | Jul 31 | 3 hrs | 2 wks | — | bar: July 2026 W3 to July 2026 W4
8 | Discussion Chapter | 7 | Aug 1 | Aug 31 | 12 hrs | 4 wks | — | bar: August 2026 W1 to August 2026 W4
8.1 | Data quality implications for pharmacy research | — | Aug 1 | Aug 15 | 5 hrs | 2 wks | — | bar: August 2026 W1 to August 2026 W2
8.2 | Health equity implications | 8.1 | Aug 16 | Aug 31 | 4 hrs | 2 wks | — | bar: August 2026 W3 to August 2026 W4
8.3 | Pipeline generalizability & future work | 8.2 | Aug 16 | Aug 31 | 3 hrs | 2 wks | — | bar: August 2026 W3 to August 2026 W4
9 | Full draft to committee | 8 | Aug 31 | Aug 31 | 2 hrs | 1 day | — | bar: August 2026 W4
REVISION
10 | Committee Feedback Incorporation | 9 | Sep 1 | Sep 30 | 10 hrs | 4 wks | — | bar: September 2026 W1 to September 2026 W4
10.1 | Incorporate Finlay feedback | — | Sep 1 | Sep 15 | 4 hrs | 2 wks | — | bar: September 2026 W1 to September 2026 W2
10.2 | Incorporate Travis & Becker feedback | 10.1 | Sep 15 | Sep 30 | 4 hrs | 2 wks | — | bar: September 2026 W3 to September 2026 W4
10.3 | Submit 2nd draft to advisor | 10.2 | Sep 30 | Sep 30 | 2 hrs | 1 day | — | bar: September 2026 W4
11 | Defense Copy Preparation | 10 | Oct 1 | Oct 31 | 8 hrs | 4 wks | — | bar: October 2026 W1 to October 2026 W4
11.1 | Final revisions & polish | — | Oct 1 | Oct 20 | 5 hrs | 3 wks | — | bar: October 2026 W1 to October 2026 W3
11.2 | Format & compile defense copy PDF | 11.1 | Oct 21 | Oct 31 | 3 hrs | 1 wk | — | bar: October 2026 W4
DEFENSE & SUBMISSION
12 | Oral Defense | 11 | Nov 4 | Nov 4 | — | 1 day | DEADLINE | bar: November 2026 W1
13 | Defense copy → honors@colorado.edu | 12 | Nov 4 | Nov 4 | — | 1 day | DEADLINE | bar: November 2026 W1
14 | Faculty recommendations due (Finlay/Travis/Becker) | 12 | Nov 6 | Nov 6 | — | 1 day | DEADLINE | bar: November 2026 W1
15 | Final copy → CU Scholar | 14 | Nov 10 | Nov 10 | — | 1 day | DEADLINE | bar: November 2026 W2
16 | Honors designation notification | — | Nov 13 | Nov 13 | — | 1 day | MILESTONE | bar: November 2026 W2
17 | December 2026 Graduation | 16 | Dec 2026 | Dec 2026 | — | — | MILESTONE
LEGEND
Registration & Data | Writing | Revision | Defense / Deadline | % Done: Complete | % Done: In Progress
KEY DEADLINES: Apr 22 = Registration due ¦ Nov 4 = Defense + copy due ¦ Nov 6 = Faculty recs ¦ Nov 10 = CU Scholar ¦ Nov 13 = Honors designation